Contract title: “Expert services within project “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”

Ref.N CB007.1.21.159 – S5

|  | Maximum |
| --- | --- |
| Organisation and methodology |  |
| Rationale | 30 |
| Degree of understanding of the Terms of Reference’s requirements (in particular its objectives and expected results) | 10 |
| Degree of understanding of the contract nature and tasks (description of the contract relevant background information) | 10 |
| Explanation of the risks and assumptions affecting the execution of the contract | 10 |
| Strategy | 40 |
| Outline of the project organization approach proposed for contract implementation. | 10 |
| Outline of the methodological approach proposed for contract implementation | 10 |
| Description of tasks for achievement of the contract objectives | 15 |
| Description of team composition, allocation of responsibilities | 5 |
| Back-up function | 10 |
| Description of the support facilities (back-stopping) that the contractor will provide during execution of the contract | 5 |
| Description of the envisaged resources to be mobilised/ description of subcontracting arrangements (if applicable) | 5 |
| Timetable of activities | 20 |
| Timetable of the activities, including timing, sequence and duration of the proposed tasks | 10 |
| Identification and timing of major milestones in executing the contract. | 10 |
| Overall total score | 100 |

| Strengths |  |
| --- | --- |
| Weaknesses |  |

NB Only tenders with average scores of at least 75 points qualify for the financial evaluation