ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	2

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	2

2.1.	Overall objective	2

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	3

3.	ASSUMPTIONS & RISKS	3

3.1.	Assumptions underlying the project	3

3.2.	Risks	3

4.	SCOPE OF THE WORK	3

4.1.	General	3

4.2.	Specific work	4

4.3.	Project management	6

5.	LOGISTICS AND TIMING	6

5.1.	Location	6

5.2.	Start date & Period of implementation of tasks	6

6.	REQUIREMENTS	7

6.1.	Staff	7

6.2.	Office accommodation	7

6.3.	Facilities to be provided by the Contractor	7

6.4.	Equipment	7

7.	REPORTS	7

7.1.	Reporting requirements	7

7.2.	Submission and approval of reports	8

8.	MONITORING AND EVALUATION	8

8.1.	Definition of indicators	8

8.2.	Special requirements	8

# BACKGROUND INFORMATION

## Partner country

Republic of Bulgaria and Republic of Serbia.

## Contracting Authority

## International Business School, Republic of Bulgaria

## Country background

The IPA II CBC Programme Bulgaria – Serbia overall aim is to stimulate the balanced and sustainable development of the Bulgaria – Serbia border region integrated in the European space – achieved through smart economic growth. The project “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people” complies with the specific objective related to priority axis 2, namely - Investing in youth, education and skills.

The project background originates from the renowned educational institutions on all levels: elementary, secondary and universities in Botevgrad and Vranje, high rate of unemployment (>15% in Vranje and ~9% in Botevgard) and lack of required skills on the labour market.

The project is highly focused on entrepreneurial learning introduction into the formal education, encompassing elementary, secondary and university schools. The aim is to strengthen employment and economic potential of the youth, contributing thereby to economic growth in the region.

The project is financed by the INTERREG IPA CBC Bulgaria – Serbia Programme and will be implemented in the period 23rd November 2016 – 22nd February 2018 in partnership with College of Applied Professional Studies, Vranje, Serbia.

## Current situation in the sector

- International Business School, as a Lead project partner is responsible for smooth management of the project and for implementation of the activities on the Bulgarian territory, as well as participation of Bulgarian part in activities on Serbian territory. One of the main tasks of the International Business School in terms of project management includes conduction of tender procedures for planned expenditures.

## Related programmes and other donor activities

N/A

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The overall objective of the project of which this contract will be a part is as follows:

The overall objective of the contract is provision of expert services for the Contracting Authority - International Business School within Project No. CB007.1.21.159: “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”; Priority Axis: Youth; Specific Objective 2.1 Skills and Entrepreneurship; Type of project: Soft, financed by the European Union, in accordance with the rules of Interreg – IPA CBC Bulgaria – Serbia Programme CCI Number 2014TC16I5CB007.

## Purpose

The purpose of this contract is as follows:

The purpose of this contract is to enable the Contract authority to implement the project by providing expert services in fields of development of learning programmes/documents/strategies; development of test materials, conducting testing and evaluation of test results; training; moderating, public speaking, facilitating services, etc.

## Results to be achieved by the Contractor

The Contractor should successfully fulfil all detail listed services in section 4, according to the specific requirements detailed in the same section of this document and should submit the required report, described in section 7.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

- Clear understanding of the contract objectives and purposes by the Contractor;

- Full cooperation between the Contracting Authority and the Contractor in view to fulfil the tasks on time, with high quality and within the budget limitation.

## Risks

Potential risks to the successful implementation of the contract include:

- Lack of necessary information;

- Lack of communication and logistical coordination between the Contractor and the Contracting Authority. In order to avoid this risk, the Contractor should show initiative and maintain continuous contact with the relevant representatives of the Contracting Authority.

- Insufficient quality of the services provided by the Contractor experts and suppliers. In order to avoid this risk the Contractor should use the most reliable and experienced staff/service providers on its disposal.

# SCOPE OF THE WORK

## General

### Description of the assignment

The aim of this contract is the expert services for the Contracting Authority - International Business School within the “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people” project, mentioned in p. 2.2 to be provided by the Contractor.

The Contractor will have to provide a variety of external expert services, expert services to test and evaluate the entrepreneurial potentials of applied participants, by preparing test materials according renowned methodology, conduct and evaluate tests and finally propose a list of the ones with best entrepreneurial skills and potential; expert services to develop entrepreneurial learning programmes with end result comprehensive teaching materials; expert services to provide teaching and training services to elementary and secondary school students, to teachers and university students; expert services to facilitate and moderate development of students companies; expert services to consult the development of models for the Entrepreneurial learning curricula for elementary and secondary schools; expert services to provide lecturer/public speaker for the Cooperation with parents/families event and for the BOND conclusion event.

### Geographical area to be covered

Botevgrad, Republic of Bulgaria and Vranje, Republic of Serbia

### Target groups

- Participants in project events – students and teachers from elementary, secondary and university schools, and parents of students;

- Educational institutions;

- Expert staff involved in project implementation;

- Visitors to project events;

- Representatives of the national and regional media;

- Local community members in the cross-border region where the project partners are located;

## Specific work

- This section individually describes the specific services to be provided by the Contractor within the implementation of project “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”.

### Expert services to test and evaluate the entrepreneurial potentials of applied participants, by preparing test materials according renowned methodology, conduct and evaluate tests and finally propose a list of the ones with best entrepreneurial skills and potential; different tests should be provided depending on education level/ age of the participants – elementary school students, secondary school students, university students, elementary and secondary school teachers. Expected by mid- September 2017 to be ready the test and conduct the test after 15th September. Due to the numerous participants expected and the large variety of educational profiles, there are expected 5 experts to conduct 1 hour testing, with 3 hours for preparation of the tests before and 8 hours for evaluation of the tests;

### Expert services to develop 2 entrepreneurial learning programmes (1 for elementary and 1 for secondary schools) with end result comprehensive teaching materials; the experts should propose the models for entrepreneurial learning integration into the curricula and document these, to participate in a 3-day session in Botevgrad and to develop comprehensive teaching material.

### The programmes should define topics to be addressed during classes, dynamics of realisation, and teaching methods and tools. The programmes should be generic to be applicable to different educational profiles and levels, but defined enough to enable effective implementation. The objective of the programme is to promote creativity, innovation and self-employment and to address: development of personal skills that are the basis of entrepreneurial behavior, raising awareness about self-employment and entrepreneurship as possible career options, work on specific entrepreneurial tasks, and provision of business skills about how to form and manage an enterprise. Expected by mid-October 2017 the 2 programmes to be developed.

### The Contractor should provide 2 experts to work 5 days on preparation, to participate 3 days in session and to prepare the teaching materials in the next 21 days;

### Expert services to provide teaching and training services to elementary school students: basic knowledge about business world, entrepreneurship and the ways of acquiring/developing competences for certain types of jobs with the goal to develop critical thinking; organizational skills for decision making, goals definition, problem solving, planning and leading; develop skills for defining, evaluation and realization of goals and objectives; skills for adjusting to new situations, ideas and technologies; develop initiative, persistence, self-confidence, learning culture etc.

### Expected elementary students: 60 in 10 elementary schools. The students from 1 school should have joint classes. Each student should have 96 school classes (72 astronomical hours). Approximately 8-12 classes per week, from mid-October 2017 until mid-January 2018. Joint classes for Bulgarian (app. 60) and Serbian (app. 65) students for 1 day in Botevgrad.

### At the end of the entrepreneurial learning for elementary schools the experts should conduct a test and ask the students to fill the satisfaction questionnaires.

### The Contractor should provide 5 experts to cover 10 elementary schools for 96 school classes (72 astronomical hours) per school (10 schools x 72 hours = 720 hours / 5 experts = 144 hours per expert);

### Expert services to provide teaching and training services to secondary school students: searching for opportunities, creative problem solving, networking, sale, interviewing, presentation, leadership, social skills and responsibility, bureaucracy, technically and financially literate for dealing with self-employment, employment and entrepreneurship that could lead to personal and career development, acquire specific business skills about how to found and manage an enterprise: to plan (business plan creation, operational planning), organize, manage, lead, analyze, inform, report, evaluate, record; to represent and negotiate; to work individually and in teams; to perform SWOT; to assess and take risks; to take initiative, act proactively and independently; to motivate and be motivated and determined for achieving goals.

### At the end of the entrepreneurial learning for secondary students the experts should conduct a test and ask the students to fill the satisfaction questionnaires.

### Expected secondary students: 30 in 3 secondary schools. The students from 1 school should have joint classes. Each student should have 120 school classes (90 astronomical hours). Approximately 12 classes per week, from mid-October 2017 until mid-January 2018. Joint classes for Bulgarian (app. 30) and Serbian (app. 30) students for 1 day in Botevgrad.

### The Contractor should provide 2 experts to cover 3 secondary schools for 120 school classes (90 astronomical hours) per school (3 schools x 90 hours = 270 hours / 2 experts = 135 hours per expert);

### To provide Train-the-Trainer experts for teachers and university students.

### Experts should educate the trainees to be skilled for transferring the knowledge to elementary, i.e. secondary school students, entrepreneurial competence and skills for teaching methods and tools, pedagogical approaches and possible testing methods to be applied with regards to the students profiles and education level, ability to induce creative, proactive, self-confident, critical, determined and responsible attitude and behavior among students, awareness of the role that inclusion of parents could have on professional orientation and entrepreneurial thinking of the students.

### Expected teachers and university students: 10 elementary teachers, 3 secondary teachers, 10 university students. Trainees should be divided into app. 4 teams. Each trainee should have 96 school classes (72 astronomical hours). Approximately 12 classes per week, from mid-October 2017 until end of December 2017. Joint classes for Bulgarian (app. 23) and Serbian (app. 29) trainees for 1 day in Vranje.

### At the end of the “Train-the-trainer” course the expert should conduct a test and ask the trainees to fill the satisfaction questionnaires.

### The Contractor should provide 2 experts to cover 4 teams, for 96 school classes (72 astronomical classes) per team (4 teams x 72 hours = 288 hours / 2 experts = 144 hours per expert);

### The Contractor should provide consultants to facilitate and moderate development of students companies.

### Consultants should consult the students' work to develop a company: propose business idea, define organizational structure, elaborate on its business plan, anticipate work outputs and simulate daily work. Students will be organized in teams and obtain different tasks for elementary and secondary schools.

### Expected 17 virtual companies to be developed by 90 students in Botevgrad, divided into teams. Approximately 8 classes per week, from December 2017 until end of January 2018.

### The Contractor should provide 6 persons to cover 13 schools for 30 school classes (22.5 astronomical hours) per consultant;

### Expert services to consult the development of models for the Entrepreneurial learning curricula for elementary and secondary schools (23 for elementary and 9 for secondary schools).

### The models should be specifically customized for each included school. Each model should define: number of classes with defined topics, school year(s) in which they will be addressed, long-term plan (during the whole school year), mid-term plan (per semesters), and short-term plan (per classes). Joint work with project team members, trained teachers will be realized on a 5-day session in Botevgrad. 32 Entrepreneurial Learning Curricula Models should be ready by mid-February 2018.

### The Contractor is to provide 2 experts to work 14 days on preparation and 5 days in session, a total of 19 days per expert;

### Expert services to provide 1 public speaker for the Cooperation with parents/families event and for the BOND conclusion event – 2 events, 2 hours each.

The content and design of all materials to be developed under this contract shall be coordinated and approved by the Contracting Authority.

The Contractor must also comply with the latest Communication and Visibility Manual for EU External Actions concerning acknowledgement of EU financing of the project. (See https://ec.europa.eu/europeaid/communication-and-visibility-manual-eu-external-actions_en. >

## Project management

### Responsible body

Responsible body for this service contract will be the Contracting Authority specified above.

### Management structure

The Contracting Authority International Business School, Botevgrad, Republic of Bulgaria and in its capacity it is responsible for conducting the current service tender procedure, signing the service contract and carrying out the overall control on the contract implementation. The day-to-day operational project implementation will be also performed by the International Business School, Botevgrad and the project team – which is responsible for implementation of project No. CB007.1.21.159: “To BOND entrepreneurial learning with primary and secondary schools and universities with the aim of curricula enhancement and entrepreneurial competences improvement for the purpose of facilitation employment of young people”; Priority Axis: Youth; Specific Objective 2.1 Skills and Entrepreneurship; Type of project: Soft, financed by the European Union, in accordance with the rules of Interreg – IPA CBC Bulgaria – Serbia Programme CCI Number 2014TC16I5CB007.

### Facilities to be provided by the Contracting Authority and/or other parties

No facilities or equipment will be provided by the Contracting Authority.

# LOGISTICS AND TIMING

## Location

The operational base for the project will be set up in Botevgrad, Bulgaria. The events will take place on the cross-border territory of Bulgaria and Serbia according to 4.1.

## Start date & Period of implementation of tasks

The intended start date is 02.09.2017 and the period of implementation of the contract will be 6 months from this date. Please see Articles 19.1 and 19.2 of the Special Conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Key experts are not required.

There is no specific evaluation criterion for the key experts but the assessment of team composition, allocation of responsibilities and experts’ inputs and outputs for proper implementation of the contract tasks is part of the assessment of the strategy.

### Other experts, support staff & backstopping

The Contractor shall select and hire other experts as required according to the needs. The selection procedures used by the Contractor to select these other experts shall be transparent, and shall be based on pre-defined criteria, including professional qualifications, language skills and work experience.

The costs for backstopping and support staff, as needed, are considered to be included in the tenderer's financial offer.

## Office accommodation

Office accommodation for each expert working on the contract is to be provided by the Contractor.

## Facilities to be provided by the Contractor

The Contractor shall ensure that experts are adequately supported and equipped. In particular it must ensure that there is sufficient administrative, secretarial and interpreting provision to enable experts to concentrate on their primary responsibilities. It must also transfer funds as necessary to support their work under the contract and to ensure that its employees are paid regularly and in a timely fashion.

## Equipment

No equipment is to be purchased on behalf of the Contracting Authority / partner country as part of this service contract or transferred to the Contracting Authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The Contractor will submit the following reports in English language:

- Draft final report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 7 days after receipt of comments on the draft final report. This report should provide conclusions and clear evidences on the implementation of all requested services. The final report must be provided along with the corresponding invoice.

The reports provided by the Contractor should be prepared in English language and submitted in the following copies:

- 1 (one) original, duly signed, stamped and dated by the legal representative of the Contractor and

- 1 (one) electronic version.

## Submission and approval of reports

The report referred to above must be submitted to the Project Manager identified in the contract. The Project Manager is responsible for approving the reports.

# MONITORING AND EVALUATION

## Definition of indicators

- Provided expert services to test and evaluate the entrepreneurial potentials of applied participants, by preparing test materials according renowned methodology, conduct and evaluate tests and finally propose a list of the ones with best entrepreneurial skills and potential as described in p .4.2.1 ;

- Provided expert services to develop 2 entrepreneurial learning programmes (1 for elementary and 1 for secondary schools) with end result comprehensive teaching materials; proposed models for entrepreneurial learning integration into the curricula and document these, and developed comprehensive teaching material by the experts as described in p. 4.2.2;

- Provided expert services for teaching and training to elementary school students as described in p. 4.2.3;

- Provided expert services for teaching and training services to secondary school students as described in p. 4.2.4.;

- Provided Train-the-Trainer experts for teachers and university students as described in p. 4.2.5;

- Provided consultants to facilitate and moderate development of students companies as described in p. 4.2.6;

- Provided expert services to consult the development of models for the Entrepreneurial learning curricula for 23 elementary and 9 secondary schools; 32 draft Entrepreneurial Learning Curricula Models; as described in p. 4.2.7.

- Provided lecturer/public speaker for the Cooperation with parents/families event and for the BOND conclusion event as described in p. 4.2.8.

## Special requirements

N/A

1 school class = 45 minutes